## Sheet1
Tasks Listed by their priority | Affiliated Engineers | Time Budget | Evaluation
Server API Users Login/Register | Tigran | Week 4
Server API schedule upload | Tigran | Week 5
Server API find carpool matches | Tigran | Week 6
User, Schedule, Sync Models | Joel | Week 4
Marshalling Models | Jesse | Week 4
Register View, Login View | Jesse | Week 4
Register Activity | Diego | Week 4
Login Activity | Diego | Week 4
Verification View | Joel | week 4
Verification Activity | Sam | Week 5
Schedule Input View | Sam | Week 5
Schedule Input Activity | Diego | Week 5
Android side api | Tigran | Week 5
Async tasks | diego | Week 5
Find matches View | Diego | Week 6
Find matches activity | Sam, Jesse | Week 6
Sync editor | Sam, Diego | Week 7
GCM Sync request | Jesse, Tigran | Week 8
Profiles View | Jesse | Week 9
Profiles Activity | Sam | Week 9
Splash screen | Joel, Diego | Week 9